## Slide 2
Index
Project Overview ​
Risk Assessment ​
Project Schedule ​
Stakeholder Management ​
Communication Management ​
Tracking and Status update ​
Project Close Out ​

## Slide 3: SCOPE, BUDGET and TIME
Design and implement a distributed analytical system using AWS Elastic Computing instances. The project is estimated to cost $1.5m with a timeline of 8 months.

## Slide 4: BUSINESS CASE
As the data grows, the current traditional data warehousing techniques cannot efficiently handle the data requirements from our functional areas, which is a threat to our strategic goals. Thus, the existing traditional data warehouse is gradually failing in handling big data within the organization.

## Slide 5: CHALLENGES
Scaling the systems linearly incurs huge software licenses and maintenance costs.
Analytical processing ability of the systems becomes increasingly inefficient as data computation is performed centrally.
Maintenance and Operations are difficult as users of the system have limited control over the infrastructure.

## Slide 6: PROPOSED SOLUTION
We proposed an implementation of a distributed analytical system on a cloud-based architecture for data processing. This solution is in line with best practices to manage efficiently the processing, storage, and analysis of big data at a lower cost.

## Slide 7: DELIVERABLES
Customize and implement an Apache Spark analytical processing engine for big data.
Implement a Hadoop distributed file system (HDFS), which makes it easy to plug in distributed analytics applications.
Construct cloud tools for implementing solutions on AWS Elastic Computing instances.

## Slide 8: FRAMEWORK: PROJECT CYCLE
Project ideas
Project Proposal
Project Completed
Concept
System Design
(Architecture)
Detailed design/
Implementation
Demo/test/
Documentation
Tech. Foundation
Capabilities
Goal
Systems analysis/
Synthesis
Project planning
Thesis proposal
Project tracking
Plan modification
Communicate
Project submission

## Slide 9: Sample project management templates and checklists have been developed for Plan, Manage and Close phases of a project
LOREM IPSUM This is dummy text it is not here to be read. This is dummy text it is not here to be read. This is dummy text it is not here to be read. This is dummy text it is not here to be read. This is dummy text it is not here to be read.
Chart: 
| 1st Qtr | 2nd Qtr | 3rd Qtr
Sales | 0.4 | 0.2 | 0.4
Project Management Tools & Templates
1. Plan
2. Manage
3. Close
Project Status Report
Issue Log
Risk Log
Deliverable Overview and Acceptance Form
Change Request Log
Action Item Log
Decision Log
Project Charter
Project Management Plan
Master Plan
Resource Plan
Organizational Change Management Plan
Communication Plan & Tracker
Quality Management Plan
Deliverable Log
Personal & Confidential Information Plan
Training Log
Kick-off Meeting Template
Phase-end Review Report and Project Closure Report

## Slide 10: PROJECT PRIORITIZATION MODELS: VENN DIAGRAM
Project Alignment
Resources
Client(s) or constituencies
Mission/Business
Venn diagrams are used to compare sets of data or ideas. They can be used to classify and/or show relationships between sets and therefore contribute to planning and prioritizing.

## Slide 11: PROJECT ORGANIZATION

## Slide 12
Engagement Plan
Milestones
Goals, Objectives & Scope
Core Team Roster
Communication Plan
High Level Training Plan
High Level Deployment Plan
Key Performance Indicators
ENGAGEMENT PLAN

## Slide 13
RACI CHART
Activity | Anchal | Nnadozie | Felix | Namratha | Roshani | Mrunali
Create Charter | A | I | I | I | I | I
Requirement Gathering | I | C | R | C | I | A
System Planning & Design | I | C | C | R | I | C
System Integration/Implementation | I | R | R | R | C | R
System Test Plan | A | I | I | I | R | C
Submit Change Request Due to Bugs or unforeseen Circumstances | A | R | R | C | I | C
Final Report | A | R | R | R | R | C

## Slide 14: SEVERITY MATRIX : PROBABILITY SCALE
On the severity matrix, we adopted values of 0.15 and 0.35 for the upper limit for a low severity risk and lower limit for a high severity risk, respectively.
Level names | Level Values (%)
Very low | 5%
Low | 10%
Medium | 40%
High | 50%
Very High | 70%

## Slide 15: RISK SEVERITY ANALYSIS
As we stated under the severity matrix, we set our upper limit for a low severity risk and lower limit for a high severity risk at 0.15 and 0.35, respectively. The risk scoring model ranked the risks as either low, medium, or high.
# Risk | Cause | Probability score | Impact score | Severity Score | Severity
1 | Loss of Critical Staff | 0.1 | 0.3 | 0.03 | Low
2 | Economic Recession | 0.1 | 0.7 | 0.07 | Low
3 | Technical Compatibility and Bug Issues | 0.7 | 0.5 | 0.35 | Medium
4 | Security and Data Integrity | 0.4 | 0.9 | 0.36 | High
5 | Design Complexity | 0.1 | 0.5 | 0.05 | Low
6 | Lack of Industry Standards | 0.1 | 0.5 | 0.05 | Low
7 | Budget Overrun | 0.5 | 0.9 | 0.45 | High
8 | Scope Creep | 0.7 | 0.7 | 0.49 | High

## Slide 16: PROJECT BUDGET
Task | Activity | Direct Cost | Overhead Cost | Total Cost
1 | Phase1(Requirement Gathering) | $150,000 | $100,000 | $250,000
2 | Phase 2 (System Plan & Design) | $160,000 | $140,000 | $300,000
3 | Phase 3 (System Development) | $170,000 | $130,000 | $320,000
4 | Phase 4 (Testing &Implementation) | $190,000 | $160,000 | $350,000
5 | Phase 5 (System Deployment) | $150,000 | $130,000 | $280,000
Project Total: |  |  |  | $ 1,500,000

## Slide 17: Percentage Complete Status for all top-level tasks. To see the status for subtasks, click on the chart and update the outline level in the Field List.
Chart: 
| Scope | Requirements Gathering/Analysis | System Planning & Design | System Development | Testing & Implementation | System Deployment
% Complete | 100 | 38 | 10 | 0 | 0 | 0
Chart: Resource Cost Summary Report
Resource | Cost
Material Components | $20000
Logistics Expenses | $15000
Facility Construction | $10000
Marketing Research Reports | $6000
Vendors | $12000
Contingency Reserve | $50,000

## Slide 18: COST DISTRIBUTION
Chart: 
| Project Manager | Senior AWS Network Analyst | Senior AWS Cloud Architect | AWS Big Data Analyst | SysOps Administrator | Management | Software Cloud | Software Big Data | Software Project Management | Software Email | Hardware | Air Travel | Meals
Actual Cost | 7200 | 0 | 9600 | 3200 | 576 | 7200 | 25000 | 0 | 40000 | 30000 | 80000 | 40000 | 0
Remaining Cost | 74400 | 116800 | 104000 | 32640 | 64064 | 0 | 75000 | 270000 | 80000 | 60000 | 80000 | 40000 | 0
Baseline Cost | 81600 | 116800 | 113600 | 35840 | 64640 | 7200 | 100000 | 270000 | 120000 | 90000 | 160000 | 80000 | 0
Chart: 
| Status: Complete | Status: Late | Status: Future Task
Cost | 93200 | 14080 | 378400
COST STATUS

## Slide 19: PROJECT RESOURCES
Hours Needed |  |  |  |  |  |  | 
Project Team Member | Phase1 | Phase2 | Phase 3 | Phase 4 | Phase 5 | Overhead Rate | Hourly Rate
Anchal | 128 | 8 | - | - | 136 | 2 | 300/hr
Felix | 16 | 160 | 240 | 96 | 72 | 1.9 | 200/hr
Nnadozie | - | 232 | 320 | - | 344 | 1.9 | 450/hr
Mrunali | 16 | 176 | 280 | 128 | 208 | 1.7 | 80/hr
Roshani | 72 | - | 200 | 80 | 96 | 1.7 | 80/hr
Namratha | 64 | 208 | 40 | 64 | 192 | 1.9 | 200/hr
Total | 296 | 784 | 1080 | 368 | 1048 | 11.1 | 1310/hr

## Slide 20: STAKEHOLDER POWER/INTEREST GRID AND KEY STAKEHOLDER LIST

## Slide 21: PROJECT MEMBERS DIRECTORY
Title | Name | Role | Department | Email | Phone
Project Manager | Anchal | Project Manager | PMO | a.bhamore@vikes.csuohio.edu | 2319761325
Chief Security Analyst | Nnadozie | Product Manager | IT | k.anyanwu@vikes.csuohio.edu | 6268171326
Senior AWS networking Analyst | Felix | Technical Manager | IT | f.asarebediako@vikes.csuohio.edu | 1275864932
Sysops Admin | Mrunali | Program Manager | PMO | m.patel46@vikes.csuohio.edu | 1236798098
AWS Big Data Analyst | Roshani | Data Scientist | IT | r.sonawane83@vikes.csuohio.edu | 9876543209
Senior AWS Cloud Architect | Namratha | Technical Lead | IT | n.shamirpet22@vikes.csuohio.edu | 3287659832

## Slide 22: COMMUNICATION MANAGEMENT MATRIX
Purpose of communication | Schedule Frequency | Media / Mechanism Used | Called by | Participant
Kickoff Meeting | Once | Zoom, Google Docs | Project Manager | Full Project Team
Report Status | Monthly | Zoom, ProjectManager.com | Anyone | Required Team Members
Team Project Proposal | Twice | Google Docs, Zoom | Project Manager | Full Project Team
Status Updates | Weekly | ProjectManager.com | Project Manager | Full Project Team
Exception/Variance Reports | As needed | WhatsApp | Anyone | Impacted team Members and Client
Configuration Changes | As changes are required/Approved | Email/ MS project | Cloud Architect | Impacted team Members and Client
Emergency or Critical events | As Needed | WhatsApp | Anyone | Full Project Team
Task Breakdown and Completion | Monthly or at the milestone | Trello | Project Manager | Full Project Team
Brainstorming and Resolving Issue | Weekly | Zoom | Data analyst and Networking Analyst | Full Project Team
Project Reviews | At milestone | Zoom and Google Docs | Project Manager | Full Project Team

## Slide 23: PROJECT TRACKING
Application used- MS project
Method to evaluate project status is Earned Value Management (EVM) and Gantt Chart
Tracking intervals are weekly and extracted data every Monday
The baseline cost of the project with 3% of project completion as of 11/27/2020 is $105,080.
The values of estimate at completion (EAC) and budget at completion (BAC) are ($1,266,680) the same, the variance at completion (difference of estimate at completion and budget at completion) is 0 as of 11/27/2020.

## Slide 24: EVALUATION AND LESSONS LEARNED
Process
Budget
Security and Data Availability
Scope creep Budget Over run
Documentation

## Slide 25: SECURITY AND DATA AVAILABILITY
Used Third Party Technology to launch Systems on cloud
No data breach, but some system downtime impacting operations and cost our project a bit
No compensation were made by the client as per SLA’s

## Slide 26
MILESTONES
Milestone | Target | Phase | Notes
Engagement Plan created | Met | Alignment/Planning | 
Discovery sessions complete | Met | Alignment/Discovery | 
Core Team readiness complete | Met | Alignment/Discovery | eLearning complete
Initial AWS configuration complete | In progress | Alignment/Validation | End of Design and Configuration
End User Orientation | Yet to meet | Alignment/Validation Launch | End of Design and Configuration
Product Launched | Yet to meet | Launch | 

## Slide 27: THANK YOU ANY QUESTIONS ?????